## Slide 1
BAS
Real-time customer onboarding for a digital bank
Reduce time-to-first-transaction from 14 days to under 5 days within 12 months and cut drop-off below 10%.
OUR OBJECTIVE
New customer onboarding takes 14 days, causing a 22% drop-off before the first transaction.
DURATION
~12 weeks (Discovery → Delivery)
ENGAGEMENT
BA-led · sponsor + SMEs · Fintech
OUTCOME
Time-to-first-transaction: 14 days → 5 days within 12 months
WHAT WILL BE DELIVERED AFTER DISCOVERY ▾
01
Discovery
Wk 1–2
FOCUS
• Frame the problem & outcome
• Map stakeholders to decisions
DELIVERABLES
• Discovery Brief
• Stakeholder Map
02
Process & BPMN
Wk 3–4
FOCUS
• Map As-Is, quantify leaks
• Design the To-Be
DELIVERABLES
• As-Is / To-Be BPMN
• Pain Point Register
03
Data & KPIs
Wk 5–6
FOCUS
• North Star & KPI tree
• Run value-leak analysis
DELIVERABLES
• KPI Tree
• Value Leak Analysis
04
Requirements
Wk 7–8
FOCUS
• Capture & slice requirements
• AC & traceability
DELIVERABLES
• Requirements Catalogue
• Stories + AC
05
Solution & Case
Wk 9–10
FOCUS
• Generate & score options
• Size costs & benefits
DELIVERABLES
• Options Matrix
• Business Case
06
Delivery & Change
Wk 11–12
FOCUS
• Sequence delivery & change
• Plan benefits realisation
DELIVERABLES
• Delivery Roadmap
• Benefits Plan
ENGAGEMENT / COST
Rate: $1,200 / day
Cadence: 4 days / week
Year-1 cost: $480k
3-YR TOTAL $820k
ROI / BENEFITS
Time-to-first-transaction
14 days → 5 days within 12 months
Annual benefit (Yr 2)
$560k
NPV (3-yr) · payback
$890k · 14 months
KEY INSIGHT
Most initiatives fail on the early decisions, not delivery. Reframing this as the decisions to be made — then running it through the chain — is what unlocks the outcome.
RECOMMENDED OPTION
Option B - Buy the SaaS ID-verification platform and integrate via middleware.
Phased: MVP first, then scale.
KEY ACTIVITIES
• Sponsor & stakeholder interviews
• SME process walkthroughs & observation
• Data profiling & benchmarks
KEY STAKEHOLDERS
• Priya Singh
• Marcus Lee
• Compliance Director
• CFO
KEY INPUTS
• Initiative brief & problem statement
• Sponsor: Head of Customer Operations
• Process: Customer onboarding
• Constraints: PSD2/Open Banking, AML/KYC, PCI DSS
EXPECTED OUTCOMES
• Decision Register
• To-Be process & fixes
• One-page business case
• Benefits realisation plan
Reduced delivery risk
Operational efficiency
Data-driven decisions
Scalable solution
Lasting adoption
Stronger outcomes
Approve $480k year-1 to cut onboarding from 14 to 5 days; NPV $890k, payback 14 months.
BAS · FINTECH